## Sheet1
Day	Finish by end of day

T 9/24	finish minimum viable product
	sum each turnstile/day
	sum each station
	scale up to multiple weeks
	what should we graph? Start to make graphs.

W 9/25	brainstorm "nice-to-haves"
	massage/clean data
	make figures
	finish slides

Th 9/26	practice presentation
	determine content, timing, speaking roles...

F 9/27	Present!